## Tasks and Timeline
Sauce & Spoon Project Plan
WBS Number | Task | Notes | Start Date | Due Date | Duration (Days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Research data on tablet menu systems and enhancements |  |  |  | 7
1.1.2 | Gather historical data on tablet menus |  |  |  | 0
1.2 | Align and evaluate stakeholder |  |  |  | 2
1.3 | Calculate projections and enhancements |  |  |  | 1
1.4 | Interview staff |  |  |  | 1
1.5 | Create project charter (scope and goals) |  |  |  | 4
1.6 | Schedule kick off meeting |  |  |  | 0
2 | Sourcing
2.1 | Research tablet menu system options |  |  |  | 4
2.2 | Generate quotes and review costs |  |  |  | 3
2.3 | Test out tablet menu system |  |  |  | 4
2.4 | Choose tablet menu system |  |  |  | 4
2.5 | Vendor timeline and deliverables schedule | Tablet service, Wifi, electrician, etc |  |  | 4
3 | Planning
3.1 | Create contracts and statements of work for vendors |  |  |  | 3
3.2 | Communicate launch date to stakehlders |  |  |  | 0
3.3 | Update project plan |  |  |  | 13
3.4 | Update marketing, social media, calender, etc |  |  |  | 10
3.5 | Create launch day plan: staffing, troubleshooting, etc. |  |  |  | 7
4 | Training
4.1 | Integrate tablet menu to existing systems | Kitchen ordering, waitlist, seating, to go |  |  | 3
4.2.1 | Train GMs on new software |  |  |  | 1
4.2.2 | Train FOH on new software | Understanding the system with legacy seating and waitlist system, help guests troubleshoot |  |  | 1
4.2.3 | Train kitchen staff/BOH on new software | Understanding the system with legacy ordering system, update menu availablilty in real time |  |  | 1
4.3 | Test run tablet menu system | Have family and friends test the system end to end on a mock launch |  |  | 1
4.4 | Create troubleshoot/support plan | GMs meet with staff to address concerns and add to troubleshooting/support plan |  |  | 5
4.5 | Launch day |  |  |  | 0

## Task Brainstorm
Task Brainstorm
WBS Number | Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1 | Project Initiation
1.1 | Research data on tablet menu systems and enhancements |  | 7 | 5 | 7 | 10 | H
1.1.2 | Gather historical data on tablet menus |  | 0 | 0 | 0 | 0 | H
1.2 | Align and evaluate stakeholder |  | 2 | 1 | 2 | 3 | H
1.3 | Calculate projections and enhancements |  | 1 | 0 | 1 | 2 | H
1.4 | Interview staff |  | 1 | 0 | 1 | 2 | H
1.5 | Create project charter (scope and goals) |  | 4 | 2 | 4 | 5 | H
1.6 | Schedule kick off meeting |  | 0 | 0 | 0 | 0 | H
2 | Sourcing
2.1 | Research tablet menu system options |  | 4 | 2 | 4 | 7 | M
2.2 | Generate quotes and review costs |  | 3 | 1 | 3 | 5 | M
2.3 | Test out tablet menu system |  | 4 | 2 | 4 | 7 | L
2.4 | Choose tablet menu system |  | 4 | 2 | 4 | 7 | L
2.5 | Vendor timeline and deliverables schedule | Tablet service, Wifi, electrician, etc | 4 | 2 | 4 | 7 | L
3 | Planning
3.1 | Create contracts and statements of work for vendors |  | 3 | 2 | 3 | 5 | H
3.2 | Communicate launch date to stakehlders |  | 0 | 0 | 0 | 0 | H
3.3 | Update project plan |  | 13 | 7 | 13 | 18 | H
3.4 | Update marketing, social media, calender, etc |  | 10 | 5 | 10 | 14 | H
3.5 | Create launch day plan: staffing, troubleshooting, etc. |  | 7 | 2 | 7 | 14 | H
4 | Training
4.1 | Integrate tablet menu to existing systems | Kitchen ordering, waitlist, seating, to go | 3 | 1 | 3 | 5 | L
4.2.1 | Train GMs on new software |  | 1 | 0 | 1 | 3 | H
4.2.2 | Train FOH on new software | Understanding the system with legacy seating and waitlist system, help guests troubleshoot | 1 | 0 | 1 | 3 | H
4.2.3 | Train kitchen staff/BOH on new software | Understanding the system with legacy ordering system, update menu availablilty in real time | 1 | 0 | 1 | 3 | H
4.3 | Test run tablet menu system | Have family and friends test the system end to end on a mock launch | 1 | 0 | 1 | 3 | H
4.4 | Create troubleshoot/support plan | GMs meet with staff to address concerns and add to troubleshooting/support plan | 5 | 3 | 5 | 7 | M
4.5 | Launch day |  | 0 | 0 | 0 | 0 | H

## Survey Questions
Survey Questions
Quality Standards Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Question Answer Options (depends on question type) |  |  |  |  | Extra Feedback Question | Extra Feedback Response (Open Ended)
[5 empty] | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Menu items ordered during visit | What was the most item type ordered? Did appetizer sales increase? | Amount of menu item types ordered | During your visit, what did you order? Choose all that apply | Multiple choice | Drinks | Appetizers | Dinner | Dessert
Number of orders per guest per visit | Do guests have multiple orders per visit? | Number or orders placed per guest per visit | Did you use the tablet to put in multiple orders while you were dining? | Yes/No | Yes | No
Overall tablet experience | Was the tablet experience positive or negative? Do the tablets positively impact guest experience? Do the tablets positively impact employee experience? | Experience rating (scaled) | On a scale of 1-5, please rate your experience with the tablet overall. | Scaled | 1 - Lacking | 2 - Mediocre | 3 - Neutral | 4 - Good | 5 - Great
Introduction/training of tablet for guests by staff | How is the triaing experience for the tablets? Employees? Guests? | Experience rating (scaled) | How well did your waiter instruct you how to use the tablet? | Scaled | 1 - Not Well | 2 - OK | 3 - Very Well
Tablet navigation experience | Does the tablet navigation offer ease of use? Is the tablet navigation appealing and engaging? | Experience rating (scaled) | On a scale of 1-5, how easy was it to use the tablet navigation? | Scaled | 1 - Difficult | 2 - Slightly Difficult | 3 - Neutral | 4 - Fairly Easy | 5 - Very Easy
Tablet experience ease | Are the tablets easy or difficult to use? Could additional training increase ease of use? Can different navigation and set up increase ease of use? | Experience rating (scaled) | How easy was it to order directly from the menu on the tablet? | Scaled | 1 - Difficult | 2 - Slightly Difficult | 3 - Neutral | 4 - Fairly Easy | 5 - Very Easy
Table wait time | Did table wait times decrease? Did table turnover time decrease? | Average amount of wait time | On average, how long did you wait for your table? | Scaled | 0-5 min. | 6-10 min. | 11-15 min. | 15+ min.
Food wait time | Did food wait time decrease? | Average amount of wait time | On average, how long did it take to receive your food order? | Scaled | 0-20 min. | 21-30 min. | 31-40 min. | 41-50 min. | 50+ min
Order accuracy | Did order accuracy increase? Did food waste decrease? | Order accuracy percentage | Did the kitchen prepare your order correctly? | Yes/No | Yes | No |  |  |  | If not, what went wrong? | -Wrong entree was brought out - Didn’t leave off the parsley - Didn’t leave off the cheese - Didn’t make the substitution I wanted - Entree was overcooked - I asked for a side of fries and got mashed potatoes
Tablet checkout experience | Was tablet check out easy and secure? | Experience rating (boolean) | How would you respond to the following sentence: “I found the checkout process quick, easy, and secure." | True/False | True | False |  |  |  | If you don't agree with the above statement, why? | - I only had cash—didn’t realize I couldn’t use it so needed the waiter - The tablet froze, so it wasn’t quick - I wanted to pay in cash so the waiter needed to process it differently - It would be faster if I could just check out with my phone
Tablet payment experience | Was the feel and confidence of tablet payment good? | Experience rating (scaled) | How confident are you in submitting your payment through a tablet? | Scaled | 1 - Not at all | 2 - Somewhat | 3 - Neutral | 4 - Confident | 5 - Very Confident
Customer engagement - newsletter | Did customers sign up? | Number of sign ups | Did you sign up for the newsletter on the tablet? | Yes/No | Yes | No
Customer engagement - Birthday Club | Did customers sign up? | Number of sign ups | Did you sign up for the Birthday Club? | Yes/No | Yes | No
Tablet experience vs traditional experience | Do customers prefer tablet service or traditional service? Do customers have a better experience with tablet servie or traditional service? | Higher chosen experience | How would you rate this experience vs. a traditional experience with a waiter? | Multiple choice | I liked the tablet experience better, and want to use it exclusively going forward. | I would liek a mix of tablet ordering and waiter interaction. | I disliked the tablets, and would rather have a waiter. | I don't have a preference
Tablet functionality experience | Did the tablets work as expected? Do technical issues disrupt experience? How can technical issues be resolved or mitigated? | Amount of tablet/technical issues | Did you have any technical issues with your tablet? | Yes/No | No | Yes |  |  |  | If yes, please describe what went wrong. | - please describe what went wrong. - The screen froze - It was glitchy - It kept freezing but after the waiter did a reboot it was fine - It froze up a couple times
Open ended customer feedback | Opportunity for customers to provide more feedback | Additional feedback | Please tell us anything else about your experience with our new tablet ordering system: | Open-ended | - The tablets were fun! - I liked the tablets - it felt like we got through our dinner faster - I liked the video about Sauce & Spoon on the tablet - The tablet was glitchy but it might’ve just been our table - Please give us the option in the future of choosing a waiter - The tablet were cool but I think we need to get used to them